## Instructions
IMPLEMENTATION GANTT CHART
Purpose
This tool provides a 6-month implementation timeline with milestones and dependencies for completing your first GloBE Information Return (GIR) filing.
Key Deadline Context
• First GIR filing deadline: June 30, 2026 (18-month extended deadline for first year)
• Subsequent years: 15 months after fiscal year end
• UK registration deadline: June 30, 2025 (6 months after first accounting period end)
• OECD Administrative Guidance confirms no filing obligations before June 30, 2026
Worksheet Overview
1. Instructions | This overview and guidance
2. Project_Setup | Project dates and configuration
3. Timeline_Summary | High-level 6-month phase overview
4. Gantt_Chart | Full 24-week task-level Gantt chart
5. Milestones | Key milestone tracking with status
6. Resource_Allocation | Time allocation by role per month
7. Critical_Path | Critical path activities and dependencies
8. Risk_Register | Project risk identification and mitigation
Color Coding (Gantt Chart)
Month 1 | Scoping and Team Mobilization
Month 2 | Data Inventory and Gap Analysis
Month 3 | System Setup and Data Extraction
Month 4 | Calculator Population and Validation
Month 5 | XML Generation and Testing
Month 6 | Filing and Confirmation
Version: 1.0 ¦ Created: December 2025 ¦ Based on OECD GIR Framework

## Project_Setup
PROJECT SETUP
MNE Group Name:
Fiscal Year End: | 31-Dec-2024
First Year in Scope?: | Yes
Filing Deadline: | 30-Jun-2026
Project Start Date: | 01-Jan-2026
Target Filing Date: | 15-Jun-2026
Project Lead:
GIR Technical Lead:
Executive Sponsor:
CALCULATED DATES
Month 1 Start:
Month 2 Start:
Month 3 Start:
Month 4 Start:
Month 5 Start:
Month 6 Start:
Project End:

## Timeline_Summary
6-MONTH TIMELINE SUMMARY
Month | Weeks | Focus Area | Key Deliverables | Status | % Complete
Month 1 | 1-4 | Scoping and Team Mobilization | Project charter, team assignments, governance structure
Month 2 | 5-8 | Data Inventory and Gap Analysis | Complete data mapping, gap register, remediation plan
Month 3 | 9-12 | System Setup and Data Extraction | Data collection templates, ERP extracts, validation rules
Month 4 | 13-16 | Calculator Population and Validation | Completed Sections 1-3, internal validation
Month 5 | 17-20 | XML Generation and Testing | Valid XML file, jurisdiction portal testing
Month 6 | 21-24 | Filing and Confirmation | Submitted GIR(s), confirmation documentation
OVERALL PROJECT PROGRESS
Phases Complete: |  | of 6
Average Completion:

## Gantt_Chart
IMPLEMENTATION GANTT CHART
ID | Phase | Task | Owner | Dep. | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
1.1 | Month 1 | Executive briefing and sponsorship | Project Lead | -
1.2 | Month 1 | Project charter development | Project Lead | 1.1
1.3 | Month 1 | Core team assembly | Project Lead | 1.2
1.4 | Month 1 | Extended team engagement | Project Lead | 1.3
1.5 | Month 1 | Constituent entity inventory | Entity Coord | 1.3
1.6 | Month 1 | Scope assessment | GIR Tech Lead | 1.5
M1 | Milestone | Month 1 complete: Team mobilized | Project Lead | 1.6
2.1 | Month 2 | Data point mapping (480 points) | Data Lead | M1
2.2 | Month 2 | Source system mapping | Data Lead | 2.1
2.3 | Month 2 | Gap identification | Data Lead | 2.2
2.4 | Month 2 | Gap categorization and impact | Data Lead | 2.3
2.5 | Month 2 | Remediation planning | Project Lead | 2.4
2.6 | Month 2 | Data request memos issued | Entity Coord | 2.5
M2 | Milestone | Month 2 complete: Gap register finalized | Data Lead | 2.6
3.1 | Month 3 | GIR Calculator setup | GIR Tech Lead | M2
3.2 | Month 3 | Data collection templates | Entity Coord | M2
3.3 | Month 3 | ERP report development | ERP/Systems | 3.1
3.4 | Month 3 | Centralized data extraction | ERP/Systems | 3.3
3.5 | Month 3 | Entity data collection (75%) | Entity Coord | 3.2
3.6 | Month 3 | Entity data collection (100%) | Entity Coord | 3.5
3.7 | Month 3 | Data validation | Data Lead | 3.6
M3 | Milestone | Month 3 complete: Data validated | Data Lead | 3.7
4.1 | Month 4 | Section 1 data entry (MNE Group) | GIR Tech Lead | M3
4.2 | Month 4 | Section 1 validation | Data Lead | 4.1
4.3 | Month 4 | Section 2 data entry (Safe Harbours) | GIR Tech Lead | 4.2
4.4 | Month 4 | Section 2 validation | Data Lead | 4.3
4.5 | Month 4 | Section 3 data entry (GloBE Comp) | GIR Tech Lead | 4.4
4.6 | Month 4 | Section 3 validation | Data Lead | 4.5
4.7 | Month 4 | Full GIR internal review | External Adv | 4.6
M4 | Milestone | Month 4 complete: GIR populated | GIR Tech Lead | 4.7
5.1 | Month 5 | Pre-generation validation | GIR Tech Lead | M4
5.2 | Month 5 | XML file generation | GIR Tech Lead | 5.1
5.3 | Month 5 | Schema validation | GIR Tech Lead | 5.2
5.4 | Month 5 | Portal access verification | GIR Tech Lead | 5.3
5.5 | Month 5 | Test environment submissions | GIR Tech Lead | 5.4
5.6 | Month 5 | Senior review | Tax Director | 5.5
5.7 | Month 5 | External advisor review | External Adv | 5.6
5.8 | Month 5 | Pre-filing checklist signed | Project Lead | 5.7
M5 | Milestone | Month 5 complete: XML ready | GIR Tech Lead | 5.8
6.1 | Month 6 | Filing sequence planning | GIR Tech Lead | M5
6.2 | Month 6 | Primary jurisdiction filing | GIR Tech Lead | 6.1
6.3 | Month 6 | Secondary jurisdiction filings | GIR Tech Lead | 6.2
6.4 | Month 6 | Submission confirmation | GIR Tech Lead | 6.3
6.5 | Month 6 | Issue resolution (if required) | GIR Tech Lead | 6.4
6.6 | Month 6 | Audit file assembly | GIR Tech Lead | 6.4
6.7 | Month 6 | Lessons learned session | Project Lead | 6.6
6.8 | Month 6 | Year 2 planning initiation | Project Lead | 6.7
M6 | Milestone | PROJECT COMPLETE: GIR Filed | Project Lead | 6.8

## Milestones
KEY MILESTONES
# | Milestone | Target Week | Target Date | Status | Actual Date | Notes
M1 | Project charter approved | Week 1
M2 | Core team assembled | Week 2
M3 | Scope assessment finalized | Week 4
M4 | Data point mapping 100% complete | Week 6
M5 | Gap register finalized | Week 7
M6 | Remediation plans approved | Week 8
M7 | GIR Calculator configured | Week 9
M8 | ERP extractions complete | Week 10
M9 | Entity data 100% collected | Week 12
M10 | Data validation completed | Week 12
M11 | Section 1-3 completed | Week 16
M12 | Full GIR internal review | Week 16
M13 | XML file generated | Week 17
M14 | Schema validation passed | Week 18
M15 | Test submissions completed | Week 19
M16 | Pre-filing checklist signed | Week 20
M17 | Primary GIR filed | Week 21
M18 | All GIRs filed | Week 22
M19 | Filing acceptance confirmed | Week 22
M20 | PROJECT COMPLETE | Week 24
MILESTONE SUMMARY
Total Milestones: | 20
Complete:
On Track:
At Risk:
Overdue:

## Resource_Allocation
RESOURCE ALLOCATION BY MONTH
Role | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Total Hours
Project Lead | 40% | 30% | 30% | 30% | 40% | 30%
GIR Technical Lead | 20% | 40% | 60% | 80% | 80% | 60%
Data Lead | 20% | 60% | 60% | 40% | 20% | 10%
ERP/Systems Lead | 10% | 20% | 40% | 20% | 10% | 5%
Entity Coordinator | 30% | 50% | 60% | 30% | 10% | 10%
External Advisor | 10% | 10% | 10% | 20% | 30% | 10%
TOTAL PROJECT HOURS
PEAK RESOURCE PERIODS
Month 3: Data Collection Peak |  | Highest demand on Entity Coordinator and Data Lead
Month 4: Calculator Completion |  | GIR Technical Lead at maximum capacity
Month 5: Filing Preparation |  | Technical Lead and Project Lead peak

## Critical_Path
CRITICAL PATH ACTIVITIES
Activities on the critical path must be completed on schedule to meet the filing deadline
Activity | Dependency | Float | Duration | Status | Impact if Delayed
Team assembly | Project approval | 1 week | 2 weeks |  | Delays all subsequent activities
Data point mapping | Team assembly | 0 days | 2 weeks |  | Cannot identify gaps without mapping
Gap remediation | Gap analysis | 0 days | 1-2 weeks |  | Missing data impacts calculations
ERP extraction | Infrastructure setup | 0 days | 2 weeks |  | Calculator cannot be populated
Section 3 completion | Sections 1-2 complete | 0 days | 2 weeks |  | XML cannot be generated
XML validation | Section 3 complete | 0 days | 1 week |  | Cannot file invalid XML
Portal submission | XML validation passed | 0 days | 1 week |  | Missed deadline, penalties
Warning: Any delay in critical path activities directly impacts the filing deadline.

## Risk_Register
PROJECT RISK REGISTER
Risk ID | Risk Description | Likelihood | Impact | Score | Mitigation | Owner
R01 | Data gaps larger than expected | High | High |  | Early gap assessment, estimation approach documented
R02 | Entity data collection delays | Medium | High |  | Regional escalation, deadline enforcement
R03 | ERP extraction issues | Medium | Medium |  | IT engagement early, backup manual extraction
R04 | Staff resource conflicts | Medium | Medium |  | Executive sponsor escalation pathway
R05 | Portal technical issues | Low | High |  | Early testing, multiple submission attempts planned
R06 | Late regulatory changes | Low | Medium |  | Monitor OECD guidance, build flexibility into timeline
R07 | Key person unavailability | Medium | High |  | Cross-training, documentation of processes
R08 | XML validation failures | Medium | Medium |  | Pre-validation testing, schema expertise
RISK MATRIX
|  | Low Impact | Medium Impact | High Impact
| High Likelihood | Medium | High | Critical
| Medium Likelihood | Low | Medium | High
| Low Likelihood | Low | Low | Medium