## Instructions
RESOURCE PLANNING WORKSHEET
Purpose
This tool helps plan and track resources required for GloBE Information Return (GIR) implementation, including internal team allocation, skills assessment, technology requirements, external advisors, and budget planning.
Based On
• OECD GIR Implementation best practices
• Tax Foundation compliance cost research (EUR 517-865M annually for European MNEs)
• Industry benchmarks: 70% of companies expect US$500,000+ annual Pillar Two compliance costs
• 50% of companies use co-sourced delivery model
Worksheet Overview
1. Instructions | This overview and guidance
2. Project_Info | Project details, scope, and timeline
3. Team_Composition | Internal team roles and FTE allocation
4. Time_Allocation | Monthly time allocation by role across 6-month timeline
5. Skills_Assessment | Skills gap analysis and action planning
6. Technology_Planning | Technology requirements and solution planning
7. External_Advisors | External advisor engagement planning
8. Budget_Summary | Comprehensive budget planning by category
9. Resource_Optimization | Strategies to optimize resource requirements
Team Size Guidelines (from Tax Foundation research)
Small MNE (10-30 jurisdictions, 50-150 entities): | 2.0-3.5 core FTE
Medium MNE (30-60 jurisdictions, 150-400 entities): | 4.0-7.0 core FTE
Large MNE (60+ jurisdictions, 400+ entities): | 7.0-11.5 core FTE
Color Coding
Yellow cells | Input cells - enter your data here
Green cells | Calculated/auto-populated cells
Version: 1.0 ¦ Created: December 2025 ¦ Based on OECD GIR Framework

## Project_Info
PROJECT INFORMATION
MNE Group Name:
Project Name: | GIR Implementation FY____
Fiscal Year:
Number of Jurisdictions:
Number of Constituent Entities:
Complexity Level:
First Year in Scope?:
Filing Deadline:
Project Sponsor:
Project Manager:
Project Start Date:
Target Go-Live Date:
OPERATING MODEL
Selected Operating Model:
Model Description:

## Team_Composition
TEAM COMPOSITION PLANNING
Define internal team roles and allocations for GIR implementation
CORE TEAM
Role | Internal FTE | External Support? | Start Date | End Date | Notes
Project Sponsor | 0.1 | N/A
Project Manager | 0.5
GIR Technical Lead | 1.0
Data Manager | 0.5
Entity Coordinator(s) | 0.5
ERP/Systems Lead | 0.3
Total Core FTE
EXTENDED TEAM (Part-time Contributors)
Role | Department | % Time Allocated | Peak Months | Key Contribution | Notes
Financial Controller | Finance | 20% | 3-4 | Financial statement data, accounting adjustments
Tax Provision Lead | Tax | 25% | 3-5 | Covered taxes data, deferred tax adjustments
Transfer Pricing Manager | Tax | 15% | 2-4 | Intra-group transaction data, adjustments
HR/Payroll Lead | HR | 10% | 2-3 | Payroll data by jurisdiction for SBIE
Fixed Assets Manager | Finance | 10% | 2-3 | Tangible asset data by location for SBIE
Legal/Company Secretary | Legal | 10% | 1-2 | Entity structure, ownership documentation
Treasury Manager | Treasury | 10% | 2-3 | FX rates, intercompany financing data
TEAM SIZE SUMMARY
Total Core FTE:
Recommended Range:

## Time_Allocation
MONTHLY TIME ALLOCATION
Based on 6-month implementation timeline (170 working hours per month)
Role | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Total Hours | Total FTE Months
Project Sponsor | 10% | 5% | 5% | 5% | 10% | 10%
Project Manager | 40% | 30% | 30% | 30% | 40% | 30%
GIR Technical Lead | 20% | 40% | 60% | 80% | 80% | 60%
Data Manager | 20% | 60% | 60% | 40% | 20% | 10%
Entity Coordinator | 30% | 50% | 60% | 30% | 10% | 10%
ERP/Systems Lead | 10% | 20% | 40% | 20% | 10% | 5%
Extended Team | 10% | 30% | 40% | 30% | 20% | 10%
TOTAL
PEAK RESOURCE PERIODS
Month 3: Data Collection Peak | Highest demand on Entity Coordinator and Data Manager
Month 4: Calculator Completion | GIR Technical Lead at maximum capacity
Month 5: Filing Preparation | Technical Lead and Project Manager peak

## Skills_Assessment
SKILLS ASSESSMENT
Assess current capabilities and identify skill gaps requiring training or external support
Skill Area | Current Capability | Gap? | Priority | Action Required
Pillar Two / GloBE Rules technical expertise
GIR structure and XML technical knowledge
Data mapping and systems integration
Project management and coordination
Multi-jurisdiction tax compliance
ETR calculation methodology
Safe harbour provisions knowledge
Transfer pricing adjustments
Financial statement / GAAP/IFRS
ERP system knowledge (SAP/Oracle)
SKILLS GAP SUMMARY
Total Skill Areas: | 10
Gaps Identified:
High Priority Gaps:
Note: Finding professionals with tax subject matter expertise is one of the top three challenges facing
tax departments. Consider 'hybrid' tax specialists who combine tax knowledge with data analytics.

## Technology_Planning
TECHNOLOGY PLANNING
Assess technology requirements and plan solutions for GIR implementation
Component | Current Solution | Gap? | Planned Solution | Implementation Date | Budget (£)
Data Repository (Central Storage) |  |  | SharePoint, Network, Cloud
Data Extraction Tool |  |  | ERP Reports, APIs, ETL
Pillar Two Calculation Engine |  |  | Excel, Commercial Platform
GIR Completion Tool |  |  | GIR Calculator (course tool)
XML Generation |  |  | Excel Export, Dedicated Tool
XML Validation |  |  | Online Validators, Desktop Tools
Filing Portal Access |  |  | Direct Portal Access
Workflow/Collaboration |  |  | SharePoint, Teams, Dedicated
Total Technology Budget
COMMERCIAL PILLAR TWO PLATFORMS (Reference)
Platform | Vendor | Key Features
CCH Integrator | Wolters Kluwer | Complete P2 calculation engine, cloud-based
Corptax GMT | CSC | OECD model rules, automated ETL
KBAT | KPMG | Cloud-based, managed services
GloBE Technology Suite | EY | SaaS or co-sourced
Pillar Two Engine | PwC | Sightline platform, AI-enhanced
Pillar Two Agent | Deloitte | Cloud platform, co-sourcing

## External_Advisors
EXTERNAL ADVISOR PLANNING
Plan external advisory engagement for GIR implementation support
Service Type | Needed? | Scope | Timing | Provider | Budget (£)
Technical Advisory |  | Pillar Two interpretation, safe harbour analysis
Implementation Support |  | Data mapping, calculator configuration
Co-sourcing/Outsourcing |  | Data collection, GIR completion, filing
Training |  | Team capability building
Quality Review |  | Independent review before filing
Total External Advisor Budget
ADVISORY COST BENCHMARKS (Reference)
Service Type | Typical Range
Technical advisory | £50,000 - £150,000
Implementation support | £100,000 - £300,000
Annual co-sourcing | £150,000 - £500,000+
Full outsourcing | £200,000 - £750,000+
ADVISOR SELECTION CRITERIA
• Pillar Two expertise and GIR filing experience
• Technology platform capabilities
• Global coverage for all filing jurisdictions
• Team stability and availability
• Pricing model (fixed vs time-based)
• Client references from similar organizations

## Budget_Summary
BUDGET SUMMARY
Comprehensive budget planning for GIR implementation
Category | Year 1 (Implementation) | Year 2+ (Ongoing) | Notes
Internal Labour |  |  | Based on FTE x fully loaded cost
Technology |  |  | One-time + ongoing licenses
External Advisory |  |  | Implementation + ongoing support
Training |  |  | Internal and external training
Travel/Expenses |  |  | Multi-jurisdiction coordination
Contingency (15-20%) |  |  | Risk buffer
TOTAL BUDGET
BUDGET BENCHMARKS BY COMPLEXITY
MNE Size | Year 1 Range | Year 2+ Range
Small (10-30 jurisdictions) | £275,000 - £500,000 | £125,000 - £250,000
Medium (30-60 jurisdictions) | £550,000 - £1,000,000 | £275,000 - £500,000
Large (60+ jurisdictions) | £1,000,000 - £1,900,000 | £500,000 - £1,000,000
BUDGET vs BENCHMARK
Your Year 1 Budget:
Complexity Level:
Status:
Note: 70% of companies expect to pay in excess of US$500,000 annually for Pillar Two compliance

## Resource_Optimization
RESOURCE OPTIMIZATION STRATEGIES
Strategies to optimize resource requirements for GIR implementation
1. LEVERAGE SAFE HARBOURS
Safe Harbour | Applicable? | Resource Impact | Action Required
Transitional CbCR Safe Harbour |  | Reduces Section 3 data requirements
QDMTT Safe Harbour |  | May reduce calculation complexity
De Minimis Exclusion |  | Reduces entity-level data requirements
2. USE TRANSITIONAL SIMPLIFIED REPORTING
OECD guidance permits simplified jurisdictional reporting (rather than CE basis)
for fiscal years beginning on or before December 31, 2028.
Potential reduction: 30-50% of entity-level data collection effort
Using Simplified Reporting?:
3. AUTOMATE WHERE POSSIBLE
Process | Manual Effort | Automation Option | Implemented?
Data extraction from ERP | High | ERP reports, APIs
Currency conversion | Medium | Automated FX feeds
Validation checks | High | Calculator built-in rules
XML generation | Medium | Export functionality
Document management | Medium | SharePoint/Teams workflows
4. BUILD REUSABLE INFRASTRUCTURE
Investment | Year 1 Cost Impact | Year 2+ Benefit | Priority
Entity master database | Higher setup | Lower maintenance
Standard data templates | Development time | Faster collection
Automated extractions | IT investment | Reduced manual effort
Documented processes | Time to document | Faster onboarding