## Instructions
DATA QUALITY ASSURANCE CHECKLIST
GloBE Information Return - Comprehensive Data Validation
PURPOSE
This checklist provides 55 actionable checkpoints to ensure GIR data quality across four dimensions:
• COMPLETENESS - All required data points are present for all entities and jurisdictions
• ACCURACY - Data values correctly reflect source system values and underlying transactions
• CONSISTENCY - Data is coherent across entities, time periods, and related data points
• TIMELINESS - Data represents the correct fiscal period with appropriate cutoffs
CHECKLIST STRUCTURE
1. Pre-Extraction Checks (10 items) - Complete BEFORE data extraction begins
2. Completeness Checks (12 items) - Verify all required data is captured
3. Accuracy Checks (15 items) - Confirm data correctness against source systems
4. Consistency Checks (10 items) - Test data coherence across entities/periods
5. Final Validation Checks (8 items) - Complete BEFORE GIR finalization
DATA QUALITY LIFECYCLE
Phase 1: PREVENTION - Define requirements, establish templates, configure validation rules
Phase 2: DETECTION - Execute completeness checks, run accuracy validation, identify anomalies
Phase 3: CORRECTION - Investigate issues, determine root cause, implement corrections
Phase 4: DOCUMENTATION - Document procedures, record resolutions, archive for audit trail
GOVERNANCE ROLES
• Pillar Two Owner - Overall GIR accuracy and filing compliance
• Data Quality Lead - Data validation process design and execution
• Entity Data Stewards - Source data accuracy for assigned entities
• Technical Lead - System extraction and transformation accuracy
• Finance Lead - Financial data reconciliation to trial balance
• HR Lead - Payroll and employee data for SBIE calculations
• Fixed Asset Lead - Tangible asset data for SBIE calculations
KEY STATISTICS
• ~480 data points required across three GIR sections
• 83% of organizations need moderate to significant data adjustments (EY 2024 Survey)
• €1 million materiality threshold for Adjusted Covered Taxes corrections
COMPLETION REQUIREMENTS
• All Critical and High severity errors must be resolved before filing
• Each checkpoint requires owner sign-off with date
• Documentation must be archived for 7-year retention period
• Final Data Quality Certification required from Pillar Two Owner
REFERENCE: Section 4.3 - Data Quality Assurance

## 1_Pre_Extraction
PRE-EXTRACTION CHECKS (10 Checkpoints)
Complete BEFORE data extraction begins - Establishes foundation for data quality
# | Checkpoint | Owner | Status | Date Completed | Verified By | Notes/Issues
1 | Entity master list reconciled to legal entity database | Entity Steward
2 | All in-scope Constituent Entities identified and documented | Pillar Two Owner
3 | Excluded entities documented with rationale per GloBE Rules | Pillar Two Owner
4 | Fiscal period confirmed (end date, duration, alignment) | Finance Lead
5 | Source systems identified for all data categories (financial, tax, HR, FA) | Technical Lead
6 | Extraction queries/reports validated on test data before production run | Technical Lead
7 | Data stewards assigned for each entity and data type | DQ Lead
8 | Extraction schedule agreed and communicated to all stakeholders | DQ Lead
9 | Currency and FX rate sources confirmed (period-end rates) | Finance Lead
10 | Period-end close confirmed complete for all entities | Finance Lead

## 2_Completeness
COMPLETENESS CHECKS (12 Checkpoints)
Ensures all required data points are present for every in-scope entity and jurisdiction
# | Checkpoint | Owner | Status | Date Completed | Verified By | Notes/Issues
11 | All CEs have identification data (legal name, TIN, tax jurisdiction) | Entity Steward
12 | All CEs have financial data extracted (trial balance, P&L) | Finance Lead
13 | All CEs have current tax expense data extracted | Tax Lead
14 | All CEs have deferred tax asset/liability data extracted | Tax Lead
15 | All jurisdictions have employee count and payroll data for SBIE | HR Lead
16 | All jurisdictions have tangible asset NBV data for SBIE | FA Lead
17 | GIR Section 1 data points complete for all required fields | DQ Lead
18 | GIR Section 2 safe harbour elections documented for eligible jurisdictions | Pillar Two Owner
19 | GIR Section 3 GloBE computation data complete for all jurisdictions | DQ Lead
20 | Intercompany transaction data captured for eliminations | Finance Lead
21 | Prior period data available for comparative analysis | Finance Lead
22 | No blank/null values in mandatory GIR fields verified | Technical Lead

## 3_Accuracy
ACCURACY CHECKS (15 Checkpoints)
Confirms extracted data correctly represents source system values and underlying transactions
# | Checkpoint | Owner | Status | Date Completed | Verified By | Notes/Issues
23 | Trial balance totals reconciled to extracted GIR data | Finance Lead
24 | Revenue figures reconciled to income statement by entity | Finance Lead
25 | Expense figures reconciled to income statement by entity | Finance Lead
26 | Current tax expense reconciled to tax provision workpapers | Tax Lead
27 | Deferred tax movements reconciled (Opening + Movement = Closing) | Tax Lead
28 | 15% cap adjustments calculated for DTAs recorded at rates > 15% | Tax Lead
29 | DTL recapture tracking implemented for 5-year monitoring (Art. 4.4.4) | Tax Lead
30 | Eligible payroll costs reconciled to payroll system totals | HR Lead
31 | Employee count (FTE) reconciled to HR records by jurisdiction | HR Lead
32 | Tangible asset NBV reconciled to fixed asset register | FA Lead
33 | Asset jurisdiction allocation verified (location vs. ownership) | FA Lead
34 | GloBE Income adjustments correctly calculated per Article 3.2 | Pillar Two Owner
35 | Adjusted Covered Taxes correctly calculated per Article 4.1 | Tax Lead
36 | SBIE phase-in rates correct for fiscal year (transitional schedule) | Pillar Two Owner
37 | ETR calculations verified for all jurisdictions (Covered Taxes / GloBE Income) | Pillar Two Owner

## 4_Consistency
CONSISTENCY CHECKS (10 Checkpoints)
Ensures data coherence across related data points, entities, time periods, and external sources
# | Checkpoint | Owner | Status | Date Completed | Verified By | Notes/Issues
38 | Intercompany transactions balance to zero after eliminations | Finance Lead
39 | Ownership percentages sum to 100% for each Constituent Entity | Entity Steward
40 | Currency conversion consistently applied (same rate source/date) | Finance Lead
41 | Accounting policies consistent across entities (revenue recognition, depreciation) | Finance Lead
42 | Year-over-year changes in entity count explained (acquisitions/disposals) | Entity Steward
43 | Year-over-year changes in revenue/profit within reasonable range | Finance Lead
44 | GIR data reconciled to published consolidated financial statements | Finance Lead
45 | GIR data reconciled to CbCR data where applicable | Tax Lead
46 | Entity classification consistent with prior year or changes documented | Pillar Two Owner
47 | Safe harbour elections consistent with eligibility analysis documentation | Pillar Two Owner

## 5_Final_Validation
FINAL VALIDATION CHECKS (8 Checkpoints)
Complete BEFORE GIR finalization - Final gate before XML generation and filing
# | Checkpoint | Owner | Status | Date Completed | Verified By | Notes/Issues
48 | All Critical and High severity errors resolved (no blocking issues) | DQ Lead
49 | Error Register reviewed and all items closed or documented | DQ Lead
50 | Reasonableness review of ETR by jurisdiction completed (0-50% expected range) | Pillar Two Owner
51 | Reasonableness review of Top-up Tax amounts completed | Pillar Two Owner
52 | All data owner sign-offs obtained (Finance, Tax, HR, FA) | DQ Lead
53 | Documentation complete for audit trail (7-year retention) | DQ Lead
54 | GIR data ready for XML generation and schema validation | Technical Lead
55 | Final Data Quality Certification signed by Pillar Two Owner | Pillar Two Owner

## Error_Register
ERROR REGISTER - Data Quality Issue Tracking
Track all identified data quality issues through to resolution - Materiality threshold: €1M aggregate for Adjusted Covered Taxes
Error ID | Description | Entity/Jurisdiction | Data Point | Severity | Status | Owner | Detected | Target Date | Resolved | Root Cause | Resolution
ERR-001 | Missing payroll data for contractors | DE GmbH | SBIE - Payroll | High | Resolved | HR Lead | 15-Feb | 17-Feb | 17-Feb | HR export excluded contractors | Re-extracted with contractors included
ERR-002 | DTL not tracked for recapture | UK Ltd | Covered Tax - DTL | Medium | Open | Tax Lead | 18-Feb | 28-Feb |  | New tracking process not implemented | Implementing DTL tracking by GL account
ERR-003 | IC imbalance €50K | US-UK pair | IC Elimination | Low | Resolved | Finance Lead | 20-Feb | 21-Feb | 21-Feb | FX rate timing difference | Adjusted to period-end rate
ERR-004
ERR-005
ERR-006
ERR-007
ERR-008
ERR-009
ERR-010

## Certification
GIR DATA QUALITY CERTIFICATION
MNE Group:
Fiscal Year:
GIR Version:
Certification Date:
SECTION CERTIFICATIONS
1. COMPLETENESS
I certify that all required data points have been collected for all in-scope
Constituent Entities and jurisdictions as required by the GloBE Rules.
Name: |  | Signature: | Date:
Title: | Data Quality Lead
2. FINANCIAL ACCURACY
I certify that the financial data has been reconciled to source systems
and validated for accuracy against trial balance and income statements.
Name: |  | Signature: | Date:
Title: | Finance Lead
3. TAX DATA ACCURACY
I certify that the current and deferred tax data is accurate and
GloBE adjustments (15% cap, DTL recapture) correctly applied.
Name: |  | Signature: | Date:
Title: | Tax Lead
4. SBIE DATA ACCURACY
I certify that eligible payroll costs and tangible asset values are
accurate and correctly allocated to jurisdictions.
Name: |  | Signature: | Date:
Title: | HR Lead / FA Lead
5. FINAL APPROVAL
I certify that the GIR data has passed all 55 data quality checkpoints
and is ready for XML generation and filing submission.
Name: |  | Signature: | Date:
Title: | Pillar Two Owner
CHECKLIST COMPLETION SUMMARY
Pre-Extraction Checks: | ___/10 Complete
Completeness Checks: | ___/12 Complete
Accuracy Checks: | ___/15 Complete
Consistency Checks: | ___/10 Complete
Final Validation Checks: | ___/8 Complete
TOTAL: | ___/55 Checkpoints
Open Errors: | ___Critical ___High ___Medium ___Low

## Dashboard
DATA QUALITY DASHBOARD
CHECKLIST COMPLETION STATUS
Section | Total Items | Complete | In Progress | Not Started | % Complete
1. Pre-Extraction Checks | 10
2. Completeness Checks | 12
3. Accuracy Checks | 15
4. Consistency Checks | 10
5. Final Validation Checks | 8
TOTAL | 55
ERROR SUMMARY
Severity | Open | In Progress | Resolved | Total
Critical
High
Medium
Low
DATA QUALITY DIMENSIONS
Dimension | Status | Key Issues
Completeness
Accuracy
Consistency
Timeliness
FILING READINESS
Criteria | Status | Notes
All Critical errors resolved
All High errors resolved
Data owner sign-offs obtained
Documentation archived
XML generation approved
OVERALL STATUS:
GO / NO-GO FOR FILING: